## 测试问题记录
编号 | 模块 | 问题描述 | 问题截图 | 问题级别 | 优先级 | 问题分类 | 测试人员 | 开发人员 | 发现时间 | 关闭时间 | 问题状态 | 备注 | 评审结果 | 修改建议
1 | 查询订购信息接口 | 接口返回字段内容与接口文档说明返回字段不一致，请确认：{ : "msg":"成功", : "code":"00000", : "data": : [ : : { : : : "appKey":"1", : : : "count":1, : : : "cycleType2":0, : : : "mobilephone":"18600000000", : : : "partnerOrderId":"1", : : : "productCode":"100101" : : } : ] 对比接口文档缺少字段： { "msg": "成功", "code": "00000", "data": [ { "appKey": "1", "count": 1, "cycleType2": 1, "invalidTime": 1498815896000, "mobilephone": "18600000000", "orderChannel": "1", "partnerOrderId": "1", "price": 1, "productCode": "1", "validTime": 1498815896000 } ] } | 已反馈 | 一般 | 中 | 功能 | 段萌 | 刘星 | 2017-07-04 |  | open
2 | 查询订购信息接口 | 10-18接口返回内容错乱（10-18：订购成功） 接口返回：{ : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"10" : } } | 已反馈 | 一般 | 中 | 功能 | 段萌 | 刘星 | 2017-07-04 |  | open
3 | 查询订购信息接口 | 数据库表t_s_order或t_s_order_record中——修改表数据为不存在的状态，接口返回不合理，待修改 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"23" : } } | 已反馈 | 一般 | 中 | 功能 | 段萌 | 刘星 | 2017-07-04 |  | open
4 | 查询订购信息接口 | 数据库表t_s_his_order_record中，初始数据orderId=1,且状态为1，调用接口返回99999异常 { : "msg":"异常", : "code":"99999", : "data":"" } | 已反馈 | 一般 | 中 | 功能 | 段萌 | 刘星 | 2017-07-04 |  | open
5 | 查询订购信息接口 | 数据库表t_s_his_order中，初始数据orderId=2,且状态为5，调用接口返回99999异常 { : "msg":"异常", : "code":"99999", : "data":"" } | 已反馈 | 一般 | 中 | 功能 | 段萌 | 刘星 | 2017-07-04 |  | open

## 测试场景
接口模块 | 链接地址 | 测试数据 | 期望结果 | 测试结果 | 备注
查询订购信息接口 | 1.http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderRecord?+参数 2.请求方式:GET 3.联通手机号码(130 131 132 145 155 156 171 175 176 185 186) 4.{"code":"10000","msg":"参数为空","data":null} {"code":"20001","msg":"非联通号码","data":null} {"code":"99999","msg":"异常","data":""} 5.涉及到的表数据——SELECT * FROM t_s_order_record | 访问链接正确，已订购后的正确联通手机号码 | 返回成功： { "msg": "成功", "code": "00000", "data": [ { "appKey": "1", "count": 1, "cycleType2": 1, "invalidTime": 1498815896000, "mobilephone": "18600000000", "orderChannel": "1", "partnerOrderId": "1", "price": 1, "productCode": "1", "validTime": 1498815896000 } ] } | 验证不通过，返回结果与接口文档不一致，待修改
|  | 访问链接正确，错误的数据 | { : "msg":"非联通号码", : "code":"20001", : "data":"" } | 验证ok
|  | 访问链接正确，无参数 | { : "msg":"参数为空", : "code":"10000", : "data":"" } | 验证ok
|  | 访问链接错误 http://120.52.120.16:51012/dtdt-rest/queryOrder/queryOrderReco?phone=14500000000 | 链接错误上报404 | 验证ok， <html><body><h1>Whitelabel Error Page</h1><p>This application has no explicit mapping for /error, so you are seeing this as a fallback.</p><div id='created'>Tue Jul 04 03:54:49 EDT 2017</div><div>There was an unexpected error (type=Not Found, status=404).</div><div>Not Found</div></body></html>
|  | 访问链接正确，未订购的正确联通号码 | { : "msg":"成功", : "code":"00000", : "data": : [ : ] } | 验证ok
|  | 访问链接正确，数据库链接异常 http://120.52.120.16:51012/dtdt-rest/queryOrder/queryOrderRecord?phone=14500000000 | { : "msg":"异常", : "code":"99999", : "data":"" } | 验证ok
|  | 访问端口错误 http://120.52.120.162:5101/dtdt-rest/queryOrder/queryOrderRecord?phone=14500000000 | 无法连接 | 验证ok，java.net.ConnectException: Connection refused: connect
|  | 访问IP地址错误 http://120.52.120.16:51012/dtdt-rest/queryOrder/queryOrderRecord?phone=14500000000 | 连接超时，无法连接 | 验证ok， java.net.ConnectException: Connection timed out: connect
|  | 访问测试路径错误 http://120.52.120.162:51012/ddt-rest/queryOrder/queryOrderRecord?phone=18600000000 | 请求异常，无返回 | 验证ok
查询可订购产品列表服务 | 1.http://120.52.120.162:51012/dtdt-rest/product/getProductList?+参数 2.请求方式:GET 3.{"code":"99999","msg":"异常","data":""} 4.涉及到的数据表——SELECT * FROM t_s_product | 访问链接正确 | 返回成功：{ "msg": "成功", "code": "00000", "data": [ { "cycleType": 0, "productCode": "000001", "productName": "包月" }, {......} ] } | 验证ok， { : "msg":"成功", : "code":"00000", : "data": : [ : : { : : : "cycleType":3, : : : "productCode":"100101", : : : "productName":"2元体验产品" : : }, : : { : : : "cycleType":0, : : : "productCode":"100102", : : : "productName":"6元包月产品" : : }, : : { : : : "cycleType":1, : : : "productCode":"100103", : : : "productName":"30元包半年产品" : : }, : : { : : : "cycleType":2, : : : "productCode":"100104", : : : "productName":"50元包年产品" : : } : ] }
|  | 访问链接错误， http://120.52.120.162:51012/dtdt-rest/product/getProductLis | 链接错误上报404 | 验证ok， <html><body><h1>Whitelabel Error Page</h1><p>This 验证ok application has no explicit mapping for /error, so you are seeing this as a fallback.</p><div id='created'>Tue Jul 04 04:07:20 EDT 2017</div><div>There was an unexpected error (type=Not Found, status=404).</div><div>Not Found</div></body></html>
|  | 访问端口错误 http://120.52.120.162:5101/dtdt-rest/product/getProductList | 无法连接 | 验证ok， java.net.ConnectException: Connection refused: connect
|  | 访问IP地址错误 http://120.52.12.162:51012/dtdt-rest/product/getProductList | 连接超时，无法连接 | 验证ok java.net.ConnectException: Connection timed out: connect
|  | 访问测试路径错误 http://120.52.120.162:51012/ddt-rest/product/getProductList | 请求异常，无返回 | 验证ok
|  | 访问链接正确，数据库链接异常 http://120.52.120.162:51012/dtdt-rest/product/getProductList | { : "msg":"异常", : "code":"99999", : "data":"" } | 验证ok
查询订单状态服务 | 1.http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?+参数 2.请求方式:GET 3.{"code":"10000","msg":"参数为空","data":null} {"code":"40010","msg":"订单不存在","data":null} {"code":"99999","msg":"异常","data":""} 4.涉及查询的表： SELECT * FROM `t_s_order`;（在途订单表） SELECT * FROM `t_s_order_record`;（产品订购关系表） SELECT * FROM `t_s_his_order_record`;（历史产品订购关系表） SELECT * FROM `t_s_his_order`;（历史在途订单表-中间流转表） | 访问链接正确+参数错误，且数据库无数据 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=34567 | { : "msg":"订单不存在", : "code":"40010", : "data":"" } | 验证ok
|  | 访问链接错误， http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderSta | 链接错误上报404 | 验证ok <html><body><h1>Whitelabel Error Page</h1><p>This application has no explicit mapping for /error, so you are seeing this as a fallback.</p><div id='created'>Tue Jul 04 05:23:04 EDT 2017</div><div>There was an unexpected error (type=Not Found, status=404).</div><div>Not Found</div></body></html>
|  | 访问端口错误 http://120.52.120.162:5112/dtdt-rest/queryOrder/queryOrderState | 无法连接 | 验证ok java.net.ConnectException: Connection refused: connect
|  | 访问IP地址错误 http://120.52.12.162:51012/dtdt-rest/queryOrder/queryOrderState | 连接超时，无法连接 | 验证ok java.net.ConnectException: Connection timed out: connect
|  | 访问测试路径错误 http://120.52.120.162:51012/ddt-rest/queryOrder/queryOrderState | 请求异常，无返回 | 验证ok
|  | 访问链接正确，数据库链接异常 http://120.52.120.162:51012/ddt-rest/queryOrder/queryOrderState | { : "msg":"异常", : "code":"99999", : "data":"" } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为1 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"未付款", : : "state":"1" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为2 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"付款中", : : "state":"2" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为3 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"付款失败", : : "state":"3" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为4 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"付款成功，待订购", : : "state":"4" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为5 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购失败", : : "state":"5" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为6 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购失败", : : "state":"6" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为7 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购失败", : : "state":"7" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为8 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购失败", : : "state":"8" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为9 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购受理中", : : "state":"9" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为10 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"10" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为11 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"11" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为12 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"12" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为13 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"13" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为14 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"14" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为15 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"15" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为16 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"16" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为17 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"17" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为18 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购成功", : : "state":"18" : } } | 验证不通过，返回结果错乱 { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"订购成功" : } }
|  | 访问链接正确+参数正确，修改订单状态为19 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"退订成功", : : "state":"19" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为20 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"退订中", : : "state":"20" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为21 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"订购作废", : : "state":"21" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为22 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"服务到期", : : "state":"22" : } } | 验证ok
|  | 访问链接正确+参数正确，修改订单状态为不存在的状态码23 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "state":"23" : } } | 验证不通过，返回结果不合理
|  | 访问链接正确+参数正确，修改订单状态为空 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"异常", : "code":"99999", : "data":"" } | 验证ok
|  | 访问链接正确+参数正确，操作表t_s_his_order_record，修改订单id为1，状态为1 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"未付款", : : "state":"1" : } } | 验证不通过 { : "msg":"异常", : "code":"99999", : "data":"" }
|  | 访问链接正确+参数正确，操作表t_s_his_order，修改订单id为1，状态为1 http://120.52.120.162:51012/dtdt-rest/queryOrder/queryOrderState?orderId=00001 | { : "msg":"成功", : "code":"00000", : "data": : { : : "stateMsg":"未付款", : : "state":"1" : } } | 验证不通过 { : "msg":"异常", : "code":"99999", : "data":"" }